Rockhampton Girls Grammar School Asbestos Removal 

Priority definitions
#1 High Priority - Key building for attention and reinstatement
#2 High – A building that is in high use and is difficult to take offline
#3 Medium – Has a defined time when work is best to be carried out
#4 Low – Not important to school operations

[bookmark: _GoBack]RGGS School Holiday periods 2012: March 31 to April 16; June 23 to July 16; September 22 to October 8; November 30 to Jan22 (2013)
RGGS Boarder Weekend and student free days – June 8 and 11, August 20, October 8.

Building availability summary
LUCK HOUSE Priority: 1 Very High  
Main functions: Ground Level – Classrooms, Level One -Boarding
Available: School holidays March 30 to April 14, September 22 to October 7.  NOT Available June 24 to July 7. 
Notes: 1) Attached or walkway to the Grant Building/Art Room.  
2) Small amount of flexibility for the alternative accommodation of boarding students for a short period. 3) Luck Building is located among many other school buildings.

JACKSON HOUSE Priority: 2 High
Function: Two Levels of Boarding (above the Library and MMP Hall which are not part of project)
Available: School Holidays- September22 to Oct 7, December1 to Jan 20 2013, NOT Available June 24 to July7.
Notes: 1) some flexibility to accommodate boarders elsewhere for a,” week or so”

GRANT Building Priority: 3 Medium
Functions: Entrance to Year 4/5 & 6 classrooms and Art Room located under the classrooms
Available: School Holidays March 30 to April 14, NOT available June 24 to July 7, September 22 to Oct 7 or week-ends.
Note: Joined to Luck building

POOL SHED Priority: 3 Medium
Functions: Change Rooms and storage for swimming pool
Available:  After March 30 until October 7.
Note: separate building adjacent to Jackson House building. Must be available again by Oct 7

P & F SHOP Priority: 3 Medium
Function: Shop run by School Parents and Friends Assoc supplying uniforms and school materials
Available: End of Term two and June Holidays -June 12 to July 10
Notes: 1) This period is when sales demand and shop stock is lowest each year.  Need to allow times to remove and replace stocks by P&F, so the shop is ready to do business by July 15. 
2) RGGS to find place to store shop stock. 3) Separate building but close to the CAB/Music building

HUMANITIES BUILDING Priority: 3 Medium
Function: Health Centre, Learning support Centre and Grounds & Maintenance
Available: School Holidays. Preferred time- September 3 to October 6th
Notes: Functions can operate from another location for a short time/period outlined.

PATERSON HOUSE Priority: 3 Medium
Function: School Administration Offices, Staff Accommodation, Boarding Dining and Kitchen
Available: School Administration Offices and Staff accommodation - December 2012 by negotiation
Available: Boarding Kitchen and Dining – School Holidays March 30 to April 14, September 22 to Oct 7 or December 2012. NOT Available June 24 to July 7
Notes: 1) Heritage Listed Building. 
2) Admin Offices and Dining and Kitchen on Ground Level 
3) Staff Accommodation and offices on first level

McKEAGUE BUILDING   Priority: 3 Medium
Function: Science Labs, Old science Labs, Assembly Hall, Senior Lockers/undercroft, toilets, kitchen/kiosk
Available:  from Nov 30 Not Available June24 to July 7
Notes: A stand-alone building containing two separate projects  
1) The assembly hall/dressing rooms/kiosk.  
2) Old science classrooms and stairwell, toilets and undercroft. 

FLORENCE HOUSE Priority: 4 Lowest / very low 
Function: Staff Accommodation
Available: Leased to staff member. Available by negotiation - December /Jan 
Note: Stand-alone building



    







